## Daily Log
Date | Task / Feature | Description | Files / Modules Touched | Status | Notes | Detailed Log
2026-09-09 | AIARAP Phase 1 DDL execution | Consolidated full DDL (80 tables, 182 FK constraints) from docs/schema/0001-phase-1-table-structures.md into one dependency-ordered script (docs/schema/aiarap_full_ddl.sql) and executed it against Amazon RDS PostgreSQL; all tables created successfully. | docs/schema/aiarap_full_ddl.sql; Amazon RDS PostgreSQL instance | Done | Schemas: global, tenant_template. Extensions: citext, uuidv7()/pg_uuidv7. | View Log
2026-09-09 | Cognito 9-pool architecture: 2 dev flows applied & verified | Designed and implemented the 9-Cognito-pool architecture (ADR-0040, supersedes ADR-0038 section 3); built and applied the 2 active dev flows (External App -> portal-dev, Support App -> support-dev) end to end: pools, resource servers, PKCE app clients, multi-pool Lambda authorizer, NLB + VPC Link + API Gateway node/dev stage. Extracted the inventory-writer module and removed a dead Terraform variable. Found and fixed a real authorizer bug (aws-jwt-verify clientId) via live CloudWatch-log-verified testing. | terraform/shared/*.tf; terraform/modules/lambda-authorizer/*; terraform/modules/tenant-onboarding/*; terraform/tenants/*; terraform/inventory/* (new); docs/adr/0040-*.md (new); AIARAP-external-app/.env; AIARAP-support-app/.env | Done | qa/prd and syscomms pools provisioned but inactive. PKCE code-exchange not yet built in either React app - login not functionally complete yet. | View Log
2026-09-09 | API Gateway decision: ADR gap analysis (research only) | Answered a sequence of questions on whether the tracked ADR set documents the AWS API Gateway decision, the AWS-vs-custom-gateway distinction, and the Node/SAP two-REST-API split. Confirmed via direct search: none of these are recorded as ADR decisions in the tracked repo - only descriptive mentions in ADR-0038/0040 and architecture-diagram.html. The actual vendor-choice reasoning (vs Kong/nginx) exists only in an untracked, non-git file outside this repo. | docs/adr/*.md (read only); docs/infra/architecture-diagram.html (read only) | Done | No files changed - research only. Follow-up offered (draft ADR-0041 for the API Gateway vendor choice + Node/SAP split), not yet requested. | View Log